## Team Dynamics
Team Dynamics |  | Team lead --> | Aiden | Secretary --> | Diego | Scrum Master --> | Kihambo
Team GitHub repo (public) | Email |  | Password
Create test user: | testuser@gmail.com |  | ******
create test admin: | testadmin@gmail.com |  | ******
Level of uncertainty
1-2 people uncertain of a technology is sus
Process for escelation
Documentation to determine team members work progress
Scrum process will help to determine this.
-document scrum process
EVERYONE IS RESPONSABLE FOR SUBMITTING ASSIGNMENTS but only teamlead will submit (ALWAYS CC REST OF TEAM ON EMAIL)
Teamlead is only figure head role, up to us to decide if the position holds authority
agree to % of work distributed to team members
COME TO AGREEMENT ON WORK DISTRIBUTION to avoid team conflict for each semester
Create an Agenda before meeting
Assign recorder/secretary to take notes
End meetings with action item
UNDERSTAND SCRUM!!!
Take time to understand it and fully commit to it
get an assignment outline reviewed to verify you are on the right track
INCLUDE: research time, testing time, costruction time, and peer review time

## Action Plan
AGENDA
Steps to succes
1 | Delegate BRD features
2 | Break down each task into a bunch of user stories
3 | Whole team decides on each task and effort point value.
4 | whole team assigns equal work
Action Item
1 | meet in usu tomorrow to finish brd and hw

## Product Backlog
Backlog ID | Priority | Context | Responsibility | Task | Expected Outcome | Effort | Status | Inside Date | Due Date
First sprint Interval 9/29 - 10/2
1 | 4 | RFP | Jacob | Scope | Accurately Depicts Product's Scope | 1 | Complete | 2023-10-02 | 2023-10-11
2 | 3 | RFP | Kihambo | Value/Purpose | Accurately Depicts Product's Value/Purpose | 1 | Complete | 2023-10-02 | 2023-10-11
3 | 3 | RFP | Kihambo | Local Musician Search | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
4 | 3 | RFP | Diego | Bingo Board | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
5 | 3 | RFP | Aiden | User Types | Accurately Depicts Product's User Types | 1 | Complete | 2023-10-02 | 2023-10-11
6 | 2 | RFP | Kihambo | Vision | Accurately Depicts Product's Vision | 1 | Complete | 2023-10-02 | 2023-10-11
7 | 2 | RFP | Diego | Gig Management | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
8 | 2 | RFP | Nathan | Artist/Venue Profile Calendar | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
9 | 2 | RFP | Diego | Basic Track Editing | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
10 | 2 | RFP | Nathan | Target Audience | Accurately Depicts Product's Target Audience | 1 | Complete | 2023-10-02 | 2023-10-11
11 | 1 | RFP | Jacob | Artist Profile Portfolio | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
12 | 1 | RFP | Aiden | Artist Collaboration Space | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
13 | 1 | RFP | Jacob | Audio Visualizer | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
14 | 1 | RFP | Nathan | Tempo Tool | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
15 | 1 | RFP | Kihambo | Ear Training | Full Feature described in Template format | 1 | Complete | 2023-10-02 | 2023-10-11
16 | 1 | RFP | ALL | Glossary | Include glossary terms and resources that you use | 0.5 | Complete | 2023-10-02 | 2023-10-11
17 | 0 | RFP | ALL | Reminding Vong of our feedback | Everyone remind Prof to help us revise | 0 | Complete | -- | --
18 | 1.5 | BRD | Aiden | BRD Format for Vong | Try to pester Vong to help us figure out BRD requirements | 1 | Complete | 2023-10-02
Second Sprint interval 10/2 - 10/4 sprint interval
19 | 4 | BRD | Aiden | first BRD draft | BRD is approved based on requirements on GitHub | 2 | Complete | 2023-10-07 | 2023-10-11
20 | 2 | Project Plan | Kihambo | first Project Plan (first half) draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-07 | 2023-10-11
21 | 2 | Project Plan | Nathan | first Project Roadmap draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-07 | 2023-10-11
22 | 2 | Project Plan | Kameron | first Risk Mitigation draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-07 | 2023-10-11
23 | 2 | Project Plan | Jacob | first Project Plan (second half) draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-07 | 2023-10-11
24 | 2 | HW | Diego | Get info on DB HW | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-07 | 2023-10-11
25 | 4 | BRD | Aiden | second BRD draft | BRD is approved based on requirements on GitHub | 2 | Complete | 2023-10-07 | 2023-10-11
Third sprint Interval 10/5 - 10/11
26 | 4 | BRD Phase 1 | Aiden | User Managements | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
27 | 3 | BRD Phase 1 | Kihambo | Collaboration Search | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
28 | 3 | BRD Phase 1 | Kihambo | Ear Training | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
29 | 3 | BRD Phase 1 | Jacob | Artist Portfolio | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
30 | 3 | BRD Phase 1 | Nathan | Tempo Tool (Metronome) | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
31 | 3 | BRD Phase 1 | Aiden | Audio Visualizer | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
32 | 3 | BRD Phase 1 | Kameron | Basic Track Editor | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
33 | 3 | BRD Phase 1 | Nathan | Artist Profile Calendar | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
34 | 3 | BRD Phase 1 | Jacob | Scale Display | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
35 | 3 | BRD Phase 1 | Diego | Bingo Board | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
36 | 3 | BRD Phase 1 | Diego | Gig Review System | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
37 | 3 | BRD Phase 1 | Kameron | Collab Feature | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-09 | 2023-10-11
38 | 2 | BRD Phase 2 |  | Music-Lesson Hub | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-10 | 2023-10-11
39 | 2 | BRD Phase 2 | Jacob | Advanced Search | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-10 | 2023-10-11
40 | 2 | BRD Phase 2 | Jacob | Tempo Transposition Tool | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-10 | 2023-10-11
41 | 2 | BRD Phase 2 |  | Rhythm Tempo Game | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-10 | 2023-10-11
42 | 5 | BRD | ALL | Get BRD Approved | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 0 | Complete | 2023-10-11 | 2023-10-11

## Burn Down Chart
Sprint Planning
Assignments |  |  |  | Mon | Tue | Wed | Thur | Fri | Mon | Tue
Backlog ID | Developer | Action Items | Initial Estimate | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-09 | 2023-10-10
|  |  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 |  | https://youtu.be/J17dOgmjS2c?feature=shared
1 | Jacob | Scope | [8 empty] | Source: | bar: Day 0 to Day 1
2 | Kihambo | Value/Purpose | Day 0: 1; Day 1: 0.5; Day 3: 0.5
3 | Kihambo | Local Musician Search | bar: Day 0; Day 2
4 | Diego | Bingo Board | bar: Day 0; Day 7
5 | Aiden | User Types | bar: Day 0; Day 2
6 | Kihambo | Vision | bar: Day 0; Day 4
7 | Diego | Gig Management | bar: Day 0; Day 7
8 | Nathan | Artist/Venue Profile Calendar | bar: Day 0; Day 4
9 | Kameron | Basic Track Editing | bar: Day 0; Day 4
10 | Nathan | Target Audience | bar: Day 0; Day 2
11 | Jacob | Artist Profile Portfolio | Day 0: 1; Day 1: 0.5; Day 4: 0.5
12 | Aiden | Artist Collaboration Space | bar: Day 0; Day 2
13 | Jacob | Audio Visualizer | Day 0: 1; Day 1: 0.5; Day 4: 0.5
14 | Nathan | Tempo Tool | bar: Day 0; Day 3
15 | Kihambo | Ear Training | bar: Day 0; Day 3
16 | ALL | Glossary | Day 0: 0.5; Day 4: 0.5
17 | ALL | Reminding Vong of our feedback | Day 0: 0
18 | Aiden | BRD Format for Vong | Day 0: 1; Day 5: 0.5; Day 6: 0.5
19 | Aiden | first BRD draft | Day 0: 2; Day 5: 2
20 | Kihambo | first Project Plan draft | Day 0: 2; Day 5: 1; Day 7: 1
21 | Nathan | first Project Roadmap draft | Day 0: 2; Day 5: 2
22 | Kameron | first Risk Mitigation draft | Day 0: 2; Day 5: 2
23 | Jacob | first Project Plan (second half) draft | Day 0: 2; Day 5: 2
24 | Diego | Get info on DB HW | Day 0: 2; Day 4: 2
25 | Aiden | second BRD draft | Day 0: 2; Day 6: 2
26 | Aiden | User Managements | Day 0: 3; Day 6: 1; Day 7: 2
27 | Kihambo | Collaboration Search | Day 0: 3; Day 3: 2; Day 5: 1
28 | Kihambo | Ear Training | Day 0: 3; Day 2: 1; Day 4: 2
29 | Jacob | Artist Portfolio | Day 0: 3; Day 7: 3
30 | Nathan | Tempo Tool (Metronome) | Day 0: 3; Day 7: 3
31 | Aiden | Audio Visualizer | Day 0: 3; Day 7: 3
32 | Kameron | Basic Track Editor | Day 0: 3; Day 6: 1; Day 7: 2
33 | Nathan | Artist Profile Calendar | Day 0: 3; Day 7: 3
34 | Jacob | Scale Display | Day 0: 3; Day 7: 3
35 | Diego | Bingo Board | Day 0: 3; Day 7: 3
36 | Diego | Gig Review System | Day 0: 3; Day 7: 3
37 | Kameron | Collab Feature | Day 0: 3; Day 7: 3
38 | ALL | Music-Lesson Hub | Day 0: 3; Day 7: 3
39 | Jacob | Advanced Search | Day 0: 3; Day 7: 3
40 | Jacob | Tempo Transposition Tool | Day 0: 3; Day 7: 3
41 | ALL | Rhythm Tempo Game | Day 0: 3; Day 7: 3
42 | ALL | Get BRD Approved | Day 0: 0
Remaining Effort |  |  | 78.5 | 76 | 71 | 66.5 | 58 | 47.5 | 43 | 0
Ideal Trend |  |  | 78.5 | 67.2857 | 56.0714 | 44.8571 | 33.6429 | 22.4286 | 11.2143 | 0

## Sprint Retrospective
What went well in the Sprint | What could be improved | What will we commit to improve in the next Sprint
Jacob: Proposal approved yay | Jacob: Having more BRD revisions | Jacob: step by step approval for speed
Kameron: I got to join another team :D | Kameron: Getting more feedback on assignments | Kameron: Finish assignments in a timely manner in order to get more feedback
Nathan: Assignments were easily understood | Nathan: work faster to get more feedback | Nathan: Coordination and using our time more effectively
Aiden: My team helped me scope out our teams priorities | Aiden: Start small and then work incrementally and exponenetially delegating along the way | Aiden: We must use our time/energy wisely/efficiently by getting the fundamental requirements approved first
Kihambo: We got approved. | Kihambo: coordination among the group. Communication can happen faster | Kihambo: communicating more efficiently
Diego: Ironing out the features and asking opinions of musicians our age was "fun" | Diego: Maintain a more uniform workflow | Diego: My sleep schedule.