## Sheet1
Backlog ID | Priority | Context | Task | Expected Outcome | Effort | Status | Due Date
Next Up
In Progress
43 | 5 | BRD | Logging | Core Requirement user story | 1 | In Progress | 2023-11-11
44 | 5 | BRD | Logout | Core Requirement user story | 1 | In Progress | 2023-11-11
45 | 5 | BRD | Authentication | Core Requirement user story | 1 | In Progress | 2023-11-11
46 | 5 | BRD | Authorization | Core Requirement user story | 1 | In Progress | 2023-11-11
47 | 5 | BRD | registration | Core Requirement user story | 1 | In Progress | 2023-11-11
48 | 5 | BRD | account recovery | Core Requirement user story | 1 | In Progress | 2023-11-11
49 | 5 | BRD | account deletion | Core Requirement user story | 1 | In Progress | 2023-11-11
50 | 5 | BRD | user management | Core Requirement user story | 1 | In Progress | 2023-11-11
51 | 5 | BRD | user privacy control | Core Requirement user story | 1 | In Progress | 2023-11-11
52 | 5 | BRD | usage analysis dashboard | Core Requirement user story | 1 | In Progress | 2023-11-11
53 | 5 | BRD | collaboration search | Features user story | 0.5 | In Progress | 2023-11-11
54 | 5 | BRD | ear training | Features user story | 0.5 | In Progress | 2023-11-11
55 | 5 | BRD | artist portfolio | Features user story | 0.5 | In Progress | 2023-11-11
56 | 5 | BRD | tempo tool | Features user story | 0.5 | In Progress | 2023-11-11
57 | 5 | BRD | audio visualizer | Features user story | 0.5 | In Progress | 2023-11-11
58 | 5 | BRD | basic track editor | Features user story | 0.5 | In Progress | 2023-11-11
59 | 5 | BRD | artist profile calendar | Features user story | 0.5 | In Progress | 2023-11-11
60 | 5 | BRD | scale display | Features user story | 0.5 | In Progress | 2023-11-11
61 | 5 | BRD | bingo board | Features user story | 0.5 | In Progress | 2023-11-11
62 | 5 | BRD | gig review system | Features user story | 0.5 | In Progress | 2023-11-11
63 | 5 | BRD | collab feature | Features user story | 0.5 | In Progress | 2023-11-11
64 | 5 | BRD | music-lesson hub | Features user story | 0.5 | In Progress | 2023-11-11
65 | 5 | BRD | advanced search | Features user story | 0.5 | In Progress | 2023-11-11
66 | 5 | BRD | tempo transition tool | Features user story | 0.5 | In Progress | 2023-11-11
67 | 5 | BRD | rhythm tempo game | Features user story | 0.5 | In Progress | 2023-11-11
68 | 4 | High Level Design Document | Client-side Architecture | Clear decision on architecture, the design aligns with goals of chosen architecture, IDs system behaviors of cross-cutting concerns, has a security design | 2.5 | In Progress | 2023-11-17
69 | 4 | High Level Design Document | Server-side Architecture | Clear decision on architecture, the design aligns with goals of chosen architecture, IDs system behaviors of cross-cutting concerns, has a security design | 2.5 | In Progress | 2023-11-17
70 | 4 | High Level Design Document | Error Handling | Defined abstractions and flow of control for error handling | 1 | In Progress | 2023-11-17
71 | 4 | High Level Design Document | Logging | Thread-safe implementation covered, 75 percent of feature behaviors covered | 1 | In Progress | 2023-11-17
72 | 4 | High Level Design Document | Data access | Save records to a relational database table, Leverages logging library to log transactions, automated tests where 75 percent of feature behaviors are covered | 1 | In Progress | 2023-11-17
73 | 4 | High Level Design Document | Security | Defined abstractions and flow of control for authentication & authorization | 1 | In Progress | 2023-11-17
74 | 3 | Project Plan | Gantt Chart | Shows that it limits critical paths(bottlenecks) while maximizing team capacity | 0.5 | In Progress | 2023-11-17
75 | 3 | Project Plan | Test Plan | a document that outlines what, how, and when a story will be tested before development | 3 | In Progress | 2023-11-17
76 | 3 | Project Plan | Site Map | figure out whats expected of site map | 2 | In Progress | 2023-11-17
77 | 3 | Project Plan | Risk Identification/Mitigation Plans | Identified worker risks, business risks, and mitigation/tolerance plans to reduce impact of risks | 1.5 | In Progress | 2023-11-17
78 | 3 | Project Plan | Purpose | Established an expected baseline for determining if our actual progress is on track, behind, or ahead | 3 | In Progress | 2023-11-17
79 | 3 | Project Plan | Audience | Identified Internal Stakeholders | 1 | In Progress | 2023-11-17
80 | 3 | Logging Library | code logging library | logging a record of executions and errors in the relational database | 10 | In Progress | 2023-11-17
81 | 3 | Data Access Library | code data access library | Accessing the data in the relational database (Read only, write only, both) | 10 | In Progress | 2023-11-17
82 | 3 | Decision Tree | Create Decision Tree | A decision tree to help with the development of the project plan | 6 | In Progress | 2023-11-17
COMPLETE
Third sprint Interval 10/5 - 10/11
26 | 4 | BRD Phase 1 | User Managements | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
27 | 3 | BRD Phase 1 | Collaboration Search | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
28 | 3 | BRD Phase 1 | Ear Training | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
29 | 3 | BRD Phase 1 | Artist Portfolio | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
30 | 3 | BRD Phase 1 | Tempo Tool (Metronome) | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
31 | 3 | BRD Phase 1 | Audio Visualizer | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
32 | 3 | BRD Phase 1 | Basic Track Editor | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
33 | 3 | BRD Phase 1 | Artist Profile Calendar | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
34 | 3 | BRD Phase 1 | Scale Display | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
35 | 3 | BRD Phase 1 | Bingo Board | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
36 | 3 | BRD Phase 1 | Gig Review System | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
37 | 3 | BRD Phase 1 | Collab Feature | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
38 | 2 | BRD Phase 2 | Music-Lesson Hub | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
39 | 2 | BRD Phase 2 | Advanced Search | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
40 | 2 | BRD Phase 2 | Tempo Transposition Tool | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
41 | 2 | BRD Phase 2 | Rhythm Tempo Game | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 3 | Complete | 2023-10-11
42 | 5 | BRD | Get BRD Approved | All user stories pertaining to feature's functionality are fleshed out according to Vong's feedback | 0 | Complete | 2023-10-11
Second Sprint interval 10/2 - 10/4 sprint interval
19 | 4 | BRD | first BRD draft | BRD is approved based on requirements on GitHub | 2 | Complete | 2023-10-11
20 | 2 | Project Plan | first Project Plan (first half) draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-11
21 | 2 | Project Plan | first Project Roadmap draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-11
22 | 2 | Project Plan | first Risk Mitigation draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-11
23 | 2 | Project Plan | first Project Plan (second half) draft | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-11
24 | 2 | HW | Get info on DB HW | Base requirements off GitHub and Notes | 2 | Complete | 2023-10-11
25 | 4 | BRD | second BRD draft | BRD is approved based on requirements on GitHub | 2 | Complete | 2023-10-11
First sprint Interval 9/29 - 10/2
1 | 4 | RFP | Scope | Accurately Depicts Product's Scope | 1 | Complete | 2023-10-11
2 | 3 | RFP | Value/Purpose | Accurately Depicts Product's Value/Purpose | 1 | Complete | 2023-10-11
3 | 3 | RFP | Local Musician Search | Full Feature described in Template format | 1 | Complete | 2023-10-11
4 | 3 | RFP | Bingo Board | Full Feature described in Template format | 1 | Complete | 2023-10-11
5 | 3 | RFP | User Types | Accurately Depicts Product's User Types | 1 | Complete | 2023-10-11
6 | 2 | RFP | Vision | Accurately Depicts Product's Vision | 1 | Complete | 2023-10-11
7 | 2 | RFP | Gig Management | Full Feature described in Template format | 1 | Complete | 2023-10-11
8 | 2 | RFP | Artist/Venue Profile Calendar | Full Feature described in Template format | 1 | Complete | 2023-10-11
9 | 2 | RFP | Basic Track Editing | Full Feature described in Template format | 1 | Complete | 2023-10-11
10 | 2 | RFP | Target Audience | Accurately Depicts Product's Target Audience | 1 | Complete | 2023-10-11
11 | 1 | RFP | Artist Profile Portfolio | Full Feature described in Template format | 1 | Complete | 2023-10-11
12 | 1 | RFP | Artist Collaboration Space | Full Feature described in Template format | 1 | Complete | 2023-10-11
13 | 1 | RFP | Audio Visualizer | Full Feature described in Template format | 1 | Complete | 2023-10-11
14 | 1 | RFP | Tempo Tool | Full Feature described in Template format | 1 | Complete | 2023-10-11
15 | 1 | RFP | Ear Training | Full Feature described in Template format | 1 | Complete | 2023-10-11
16 | 1 | RFP | Glossary | Include glossary terms and resources that you use | 0.5 | Complete | 2023-10-11
17 | 0 | RFP | Reminding Vong of our feedback | Everyone remind Prof to help us revise | 0 | Complete | --
18 | 1.5 | BRD | BRD Format for Vong | Try to pester Vong to help us figure out BRD requirements | 1 | Complete